## Backlog
ID | Category | Name | User Story | Completion Requirement | Priority | Sprint | Implementation Plan | Date Completed
1 | Physics | Physics System | User is constrained by physics properties such as gravity. | Implement Farseer Physics Engine support for game objects. | 10 | 1 | Use Farseer Physics Engine. | 2010-10-11
2 | Input | Input Component | User presses keys/buttons or manipulates joystick to interact with game. | Implement InputComponent. | 8 | 2 | Use InputHelper class (still need to make modifications to the class). | 2010-10-21
3 | Physics | PhysicsComponent | Game object has appropriate physics. | Implement PhysicsComponent. | 10 | 2 | The physics component should be re-usable, and will be backed by the Farseer engine. Basically, this component should contain Fixture information/variables, so we always have the position in the physics world of each object that has this physics component. Then other components can retrieve the position of the Fixture's Body variable. | 2010-10-31
5 | Lights | GravityLightComponent | Light modifies gravity in the area covered by its light. | Implement the component. | 10 | 2 | Attach lighting and physics components to a light object. Then, check the game world to see which objects are in the light given by the light component, and apply upward force to each object until the light is no longer touching the objects. | 2010-11-09
6 | Characters | Player Component | User moves character, which can jump and walk on surfaces. | Implement PlayerComponent. | 10 | 2 | Create a player component that can draw itself, and add a physics component that keeps track of position for the drawing. | 2010-10-31
7 | Lights | NullLight | Light nulls the effects of all other lights in the area covered by its light. | Implement the component. | 10 | 4 | Create a light component that utilizes an EffectEnabled/LightColor property to null the effects of other light components in the Level's list of light components. If the light is touching the LightPosition of the other light, the other light's color should change to the color of this light component, and either the effect should be turned off or it's function should be changed out with the strategy pattern. | 2010-11-09
16 | Audio | AudioComponent | User hears music and sound effects. | Implement the component. | 10 | 5 | Use XACT and related libraries to implement another component that can be contacted by other components with a message telling the component which sound to play, how to manipulate volume, and other important actions as defined. | 2011-01-12
18 | Configuration | Configuration File and Objects. | User sees configuration file that can be edited. | Impement or integrate a config file system. | 10 | 5 | Integrate EasyConfig and write configuration files for all game data that should be easily tweakable from outside the game. | 2011-01-12
4 | Graphics | Light | User sees lights emitted from game objects. | Implement lighting scheme. | 10 | 6 | Create a shadow image for each object emitting light that shows a black/white representation of the lighting in the scene that takes into account the effect of other objects in the scene creating shadows. Then, blend them all together with the appropriate colors and display this information on the background, which will create a dynamic 2D lighting effect. | Completed, but created compatibility issues and had to be removed.
10 | Lights | SpeedLight | Light modifies the speed of objects touched by its light. | Implement the component. | 10 | 7 | Create a component that provides a multiplier for components to use when deciding the force that is moving them, so that speed can be modified by the light for any object that its touching. | 2011-03-11
8 | Lights | PlatformLight | Light projects a light platform in the area/direction it is pointed. | Implement the component. | 10 | 8 | Create a LightPlatform class that is created and easily manipulated by a PlatformLight. The LightPlatform class should have a platform variable and be able to move its position, making it a dynamic in the physics world, and should be able to determine the position of the platform in the game world. This calls for a platform class that will make this easy.
15 | Physics | MovingPlatformComponent | User can utilize a platform that moves between a collection of points with a certain velocity. | Implement the component. | 10 | 8 | Create a PhysicsComponent that is pushed from point to point in a list of destinations with application of forces, creating a moving platform.
21 | Lights | PlayerControllableLight | User uses keys or the right Xbox control stick to aim a light in the direction indicated by the input. | Implement an interface to lights that are marked interactive so that player input can be used to manipulate them. | 5 | 8 | Create a new boolean light property that marks whether or not a light is interactive. If the player activates it with a button press or something, then utilize player input to decide which direction the light is facing.
20 | Player | Health | User sees player character get hit and the screen is covered by a blur effect whose intensity is related to the amount of player health left. | Activate BlurPostProcessing component (already implemented) and tune its intensity according to player health. | 8 | 8 | Activate the post-processing component that is already a part of the project and call its functions at the appropriate time each Draw() so that the post-processing effects are applied to the entire game scene (call it after everything else has been drawn).
14 | Scenes | Level 1 - Introduction | User plays through tutorial level explaining game mechanics in an intuitive way. | Create introduction scene. | 9 | 8 | Define introductory level in Tiled and script events. Tutorial text can be hidden in the level's darkness and read with a light.
22 | Bugs | Bug Fixes | User does NOT experience bugs. | Fix as many bugs logged on GitHub as possible. | 10 | 9 | Fix bugs according to individual bug requirements.
23 | Symposium Demo | Symposium Demo | User is able to pick up game and play from any point in the introductory level. | Ensure that the symposium demo works as expected on PC and Xbox platforms. | 10 | 9 | Run through symposium demo and have friends test for bugs.
19 | Scripting | Scripting | User sees dynamic and interesting effects, camera movements, etc. | Create scripting mechanism. | 9 | N/A | Write a script manager that accepts scripts and plays them in the game world, so that camera movements and effects and sounds can be defined outside the game code. This includes complete cinematic moments in which the user does nothing but watch certain events unfold. | Cancelled
9 | Lights | FrictionLight | Light modifies the friction coefficient of surfaces covered by its light. | Implement the component. | 10 | N/A | ? | Cancelled
12 | Artificial Intelligence | Non-Playable Character Intelligence | User sees NPCs acting on needs and according to different moods (levels of aggression). | Implement AIComponent and some EnemyComponents. | 7 | N/A | ? | Cancelled
13 | Particle Effects | ElectricityParticleEffect | User sees electricity particle effect similar to the visible electricity in a tesla coil system. | Implement electricity particle effect. | 8 | N/A | ? | Cancelled