## Backlog
ID | Category | Name | User Story | Completion Requirement | Priority | Sprint | Implementation Plan | Date Completed
1 | Physics | Physics System | User is constrained by physics properties such as gravity. | Implement Farseer Physics Engine support for game objects. | 10 | 1 | Use Farseer Physics Engine. | 2010-10-11
2 | Input | Input Component | User presses keys/buttons or manipulates joystick to interact with game. | Implement InputComponent. | 8 | 2 | Use InputHelper class (still need to make modifications to the class). | 2010-10-21
3 | Physics | PhysicsComponent | Game object has appropriate physics. | Implement PhysicsComponent. | 10 | 2 | The physics component should be re-usable, and will be backed by the Farseer engine. Basically, this component should contain Fixture information/variables, so we always have the position in the physics world of each object that has this physics component. Then other components can retrieve the position of the Fixture's Body variable. | 2010-10-31
5 | Lights | GravityLightComponent | Light modifies gravity in the area covered by its light. | Implement the component. | 10 | 2 | Attach lighting and physics components to a light object. Then, check the game world to see which objects are in the light given by the light component, and apply upward force to each object until the light is no longer touching the objects. | 2010-11-09
6 | Characters | Player Component | User moves character, which can jump and walk on surfaces. | Implement PlayerComponent. | 10 | 2 | Create a player component that can draw itself, and add a physics component that keeps track of position for the drawing. | 2010-10-31
7 | Lights | NullLight | Light nulls the effects of all other lights in the area covered by its light. | Implement the component. | 10 | 3 | Create a light component that utilizes an EffectEnabled/LightColor property to null the effects of other light components in the Level's list of light components. If the light is touching the LightPosition of the other light, the other light's color should change to the color of this light component, and either the effect should be turned off or it's function should be changed out with the strategy pattern.
8 | Lights | PlatformLight | Light projects a light platform in the area/direction it is pointed. | Implement the component. | 10 | 3 | Create a LightPlatform class that is created and easily manipulated by a PlatformLight. The LightPlatform class should have a platform variable and be able to move its position, making it a dynamic in the physics world, and should be able to determine the position of the platform in the game world. This calls for a platform class that will make this easy.
11 | Lights | Component Interaction | Light Component effects can combine to create dynamic light combinations at runtime. | Implement interaction system for all of the Sprint 1 components so that their effects combine and stack appropriately. | 10 | 3 | Create a light communication system. A class called something like LightManager should provide easy access to all light fields for all other light fields. This way, they can access properties like LightingEnabled, EffectEnabled, LightDistance, LightBrightness, and so forth. Then all lights will be able to manipulate each other at runtime depending on their circumstances. One idea is to implement the LightEffect with a strategy pattern so that light functions can be easily swapped. This could come in useful when the null light touches other lights, because then at that point the null light could convert the light to its functionality instead of modifying individual light properties. There are reasons I'd want to do both things though, so I don't know how useful utilizing the pattern would be. But it would make changing lights to something entirely different really easy, which is something I'll probably want to do.
4 | Graphics | Light | User sees lights emitted from game objects. | Implement lighting scheme. | 10 |  | Create a shadow image for each object emitting light that shows a black/white representation of the lighting in the scene that takes into account the effect of other objects in the scene creating shadows. Then, blend them all together with the appropriate colors and display this information on the background, which will create a dynamic 2D lighting effect. | Completed, but created compatibility issues and had to be removed.
9 | Lights | FrictionLight | Light modifies the friction coefficient of surfaces covered by its light. | Implement the component. | 10
10 | Lights | SpeedLight | Light modifies the speed of objects touched by its light. | Implement the component. | 10
12 | Artificial Intelligence | Non-Playable Character Intelligence | User sees NPCs acting on needs and according to different moods (levels of aggression). | Implement AIComponent and some EnemyComponents. | 7
13 | Particle Effects | ElectricityParticleEffect | User sees electricity particle effect similar to the visible electricity in a tesla coil system. | Implement electricity particle effect. | 8
14 | Scenes | Level 1 - Introduction | User plays through tutorial level explaining game mechanics in an intuitive way. | Create introduction scene. | 9