## Project Backlog
ID | Category | Name | User Story | Completion Requirement | Priority | Sprint | Implementation Plan | Date Completed
| Physics | Physics System | User is constrained by physics properties such as gravity. | Implement Farseer Physics Engine support for game objects. | 10 | 1 | Use Farseer Physics Engine. | 2010-10-11
| Input | Input Component | User presses keys/buttons or manipulates joystick to interact with game. | Implement InputComponent. | 8 | 2 | Use InputHelper class (still need to make modifications to the class). | 2010-10-21
| Physics | PhysicsComponent | Game object has appropriate physics. | Implement PhysicsComponent. | 10 | 2 | The physics component should be re-usable, and will be backed by the Farseer engine. Basically, this component should contain Fixture information/variables, so we always have the position in the physics world of each object that has this physics component. Then other components can retrieve the position of the Fixture's Body variable.
| Graphics | Light | User sees lights emitted from game objects. | Implement lighting scheme. | 10 | 2 | Create a shadow image for each object emitting light that shows a black/white representation of the lighting in the scene that takes into account the effect of other objects in the scene creating shadows. Then, blend them all together with the appropriate colors and display this information on the background, which will create a dynamic 2D lighting effect.
| Lights | GravityLightComponent | Light modifies gravity in the area covered by its light. | Implement the component. | 10 | 2 | Attach lighting and physics components to a light object. Then, check the game world to see which objects are in the light given by the light component, and apply upward force to each object until the light is no longer touching the objects.
| Characters | Player Component | User moves character, which can jump and walk on surfaces. | Implement PlayerComponent. | 10 | 3 | Create a player component that can draw itself, and add a physics component that keeps track of position for the drawing.
| Lights | NullLightComponent | Light nulls the effects of all other lights in the area covered by its light. | Implement the component. | 10 | 3
| Lights | PlatformLightComponent | Light projects a light platform in the area/direction it is pointed. | Implement the component. | 10 | 3
| Lights | FrictionLightComponent | Light modifies the friction coefficient of surfaces covered by its light. | Implement the component. | 10 | 3
| Lights | SpeedLightComponent | Light modifies the speed of objects touched by its light. | Implement the component. | 10 | 3
| Lights | Component Interaction | Light Component effects can combine to create dynamic light combinations at runtime. | Implement interaction system for all of the Sprint 1 components so that their effects combine and stack appropriately. | 10 | 3
| Artificial Intelligence | Non-Playable Character Intelligence | User sees NPCs acting on needs and according to different moods (levels of aggression). | Implement AIComponent and some EnemyComponents. | 7 | 3
| Particle Effects | Electricity Particle Effect | User sees electricity particle effect similar to the visible electricity in a tesla coil system. | Implement electricity particle effect. | 8 | 4
| Scenes | Introduction | User plays through tutorial level explaining game mechanics in an intuitive way. | Create introduction scene. | 9 | 4