## Sheet1
ID | Category | Name | User Story | Completion Requirement | Priority | Sprint | Implementation Plan | Estimated Hours
15 | Physics | MovingPlatformComponent | User can utilize a platform that moves between a collection of points with a certain velocity. | Implement the component. | 10 | 5 | Create a PhysicsComponent that is pushed from point to point in a list of destinations with application of forces, creating a moving platform. | 5
16 | Audio | AudioComponent | User hears music and sound effects. | Implement the component. | 10 | 5 | Use XACT and related libraries to implement another component that can be contacted by other components with a message telling the component which sound to play, how to manipulate volume, and other important actions as defined. | 5
18 | Configuration | Configuration File and Objects. | User sees configuration file that can be edited. | Impement or integrate a config file system. | 10 | 5 | Integrate EasyConfig and write configuration files for all game data that should be easily tweakable from outside the game. | 5
14 | Scenes | Level 1 - Introduction | User plays through tutorial level explaining game mechanics in an intuitive way. | Create introduction scene. | 9 | 5 | Define introductory level in Tiled and script events. | 10
19 | Scripting | Scripting | User sees dynamic and interesting effects, camera movements, etc. | Create scripting mechanism. | 9 | 5 | Write a script manager that accepts scripts and plays them in the game world, so that camera movements and effects and sounds can be defined outside the game code. This includes complete cinematic moments in which the user does nothing but watch certain events unfold. | 20
4 | Graphics | Light | User sees lights emitted from game objects. | Implement lighting scheme. | 10 | 5 | Create a shadow image for each object emitting light that shows a black/white representation of the lighting in the scene that takes into account the effect of other objects in the scene creating shadows. Then, blend them all together with the appropriate colors and display this information on the background, which will create a dynamic 2D lighting effect. | 5